## Sheet1
Activity
Activity | Wat is to be done | Start Date and Time | End Date and Time | Notes and Comments
Requirements Analysis | Understand from the Club Members the requirments for the creation / Improvement of the Web Application. What the new features are abd how they will be used | Monday 22nd May 8:00am | Wednesday 24tht May 5:00pm | 3 Days allocated to nail down the requirments. Ths time will allow all members to have their say and be comfortable they were conculted
Specification | From the requirments provided, decisions need to be made on how to build and represent those requirments. This will include what software to use to contain and create the we application. What the web app will look like, by layout, text size and colour, pictures | Thursday 25th May 8:00am | Thursday 25th May 5:00pm | 1 Day to deicde on the new layout and software to be used to crete the Web Application
Create the Project | Decide on how the Web Application will be created and realeased for User Acceptance Testing. Once Done the Web Application can be created as per User requirement. Full testing plan and docuemntation should be maintained through out the process so maintenance can be easily done when required and there are no unknown show stoppers | Friday 26th May 8:00 | Friday 2nd May 5:00pm | 7 Days allocated for the buildig of the new Web Application. This time will take up all the tasks from creating the layout on the web page, writing the code and uploading any photographs or pictures.
Testing | Once completed, project can be released for User Acceptance Testing. This process can be a repeated back and forth as the testing uncovers any bugs, issues or changes which need to be addressed and resolved | Monday 5th May 8:00 | Friday 9th May 5:pm | 5 Days allocated to complete the testing but also rectifiy any identified bugs orchnage requests
Training and Support | Once the Testing is completed and the Application is ready for production. Training and Support resources need to be provided so that users can get to know the changes in acceptable time frame | Monday 12th 8:00am | Tuesday 13th May 5pm | Any training documents created and made available for the club members
Risks
Risk event | Impact | Mitagation Steps | Severity (1 - 5)
In fighting | Changes to a shared entity can casuse issues. People do not always like change | Communication - keep all stkeholders informed | 1
Outage | While the website is being upgraded it will be unavailable online | Make sure all members are aware of the outage. Provice a time frame for the outage so they know when it will be back online | 3
No online presence | This could mean that there are no advertised means of being contacted. This could affect the bottom line | Contact exisiting customers and stakeholders and provide another means of communication | 4
Expecations not met | Members may lose confidence or feel shot changed | Make sure all members are educated with the changes being made | 1